## RACI
Role / Project Deliverable | Deal Team | Portfolio Managers | Exit Planning Committee | CIO | Legal | Risk | Compliance | Data Governance | Finance | Valuation | Data Engineers | Solution Architects | BI Developers | Application Developers
| Front Office / Business Teams |  |  | Leadership | Risk, Legal, and Governance Teams |  |  |  | Finance and Valuation Teams |  | Technology Teams
Module 1: Deal Sourcing and Due Diligence | R | - | - | A | C | - | C | - | - | - | R/C | R/C | - | -
Module 2: Portfolio Management | - | R | - | A | - | I | I | C | - | - | R | - | R | -
Module 3: Exit Planning | R | - | R | A | I | - | I | - | R/C | R/C | R | - | - | R

## GANTT
ACTIVITIES | PRIORITY | SPRINT # | STORY POINTS | WEEKS
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Feature 1: Automating Data Integration | 1
Discovery and backlog refinement. Define integration requirements, confirm external provider APIs (e.g., PitchBook). |  | 0 | 5 | bar: WEEKS 1 to WEEKS 2
Assumption Story Points: Handling currency translation rules in integration pipelines. |  | 0 | 8
Assumption Story Points: Introducing unique identifiers (FUND_ID, COMPANY_ID) to replace text joins. |  | 0 | 5
Assumption Story Points: Defining data refresh frequency standards. |  | 0 | 3
Develop ETL pipelines for data ingestion, establish data staging environment. |  | 1 to 2 | 13 | bar: WEEKS 3 to WEEKS 6
Implement data quality and lineage module (validation rules, error handling, audit logs). |  | 3 to 4 | 13 | bar: WEEKS 7 to WEEKS 10
Integrate pipelines with ILMP core database and conduct end-to-end test with sample data. |  | 5 | 8 | bar: WEEKS 11 to WEEKS 12
ACTIVITIES | PRIORITY | SPRINT # | STORY POINTS | WEEKS 1: WEEKS
|  |  |  | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Feature 2: Centralised Document Repository | 2
Requirements refinement, repository architecture design, metadata schema definition. |  | 6 to 7 | 13 | bar: WEEKS 13 to WEEKS 16
Develop repository within ILMP, enable tagging, version control, and permissions. |  | 8 to 9 | 13 | bar: WEEKS 17 to WEEKS 20
Integrate with deal sourcing workflow (upload and retrieval). |  | 10 | 8 | bar: WEEKS 21 to WEEKS 22
Compliance workflow integration for approvals and audit logs. |  | 11 | 8 | bar: WEEKS 23 to WEEKS 24
ACTIVITIES | PRIORITY | SPRINT # | STORY POINTS | WEEKS 13: WEEKS
|  |  |  | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Feature 3: Dynamic Portfolio Dashboard | 3
Finalise KPI definitions (EBITDA growth, fund vs sector, drill-down structure) |  | 12 | 5 | bar: WEEKS 25 to WEEKS 26
Assumption Story Points: Addressing weighting methodology choice (market value vs EBITDA-based). |  | 12 | 5
Assumption Story Points: Ensuring alignment with ILPA or internal reporting standards. |  | 12 | 3
Build dashboard prototype using fund and company metrics datasets. |  | 13 to 14 | 13 | bar: WEEKS 27 to WEEKS 30
Deploy interactive dashboards with filters (fund, sector, company). |  | 15 | 8 | bar: WEEKS 31 to WEEKS 32
User Acceptance Testing with CIO and Portfolio Managers. |  | 16 | 5 | bar: WEEKS 33 to WEEKS 34
ACTIVITIES | PRIORITY | SPRINT # | STORY POINTS | WEEKS 25: WEEKS
|  |  |  | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Feature 4: Exit Planning Enhancements | Secondary Scope
Requirements refinement with Deal Team and Finance. Identify valuation templates and reporting needs. |  | 17 | 5 | bar: WEEKS 37 to WEEKS 38
Automate valuation models, embed into ILMP workflow. |  | 18 to 19 | 13 | bar: WEEKS 39 to WEEKS 42
Integrate exit report templates, generate test outputs. |  | 20 | 8 | bar: WEEKS 43 to WEEKS 44
Compliance and audit validation. |  | 21 | 5 | bar: WEEKS 45 to WEEKS 46